Plasticity Spark Grant – End Report

The plasticity spark grant was assembled in an attempt to develop an interdisciplinary research line about plasticity. It includes people from diverse backgrounds, from plant biology and biophysics through brain sciences, chemistry, and metabolism to social sciences and philosophy.

When we structured the grant, we thought it would be easy – one meeting to get to know the participants, then another to develop an idea of how to work together, and from there to the meat of the subject. That is, we thought that we would be able to start with some actual exploration of the implementation of our research idea through internal discussions and interactions with other societal stakeholders.

However, very soon, we found out that we were not realistic in our expectations. We still had to go through a long way. We had to find a good idea for a research question, which was not straightforward.

Why?

Several reasons. First, there are the common issues in an endeavor such as this one: (i) we are trying to construct an unusual collaboration, and it takes time to establish an unusual collaboration; (ii) we did not know each other well, and it takes time to develop trust that promote collaboration; (iii) we have some background issues – we come from different disciplines and might not understand each other fully.

However, much more important than that, we were trying to construct a research project around a concept rather than around a specific scientific question. We do not want to study something like 'Climate Change,' 'Discrimination in Society,' or 'How to Fight Disease X.' We want to understand how a specific concept – that of plasticity is used in different parts of science. And, we want to know how this understanding can promote a batter social resilience in our accelerated society.

But how does a scientist or a group of academic scholars achieve this goal? We had to think hard (and, in fact, until now, we are not sure that we know). We conducted a brainstorming session moderated by two talented moderators from the Flatland agency - Niva van de Geer and Lucas … Many ideas came up in the meeting. It was suggested that we could frame research into plasticity around one unified theme. For example, can we think about plasticity across our different fields and backgrounds as all connected to Coffee? We did not know!

So, we decided to change course. Instead of jumping directly into the water, we decided to stay and explore the shoreline. In other words, we decided to replace our original plan with a series of meetings where we will explore the possibilities of studying plasticity.

Luckily, we had our two moderators that agreed to work with us, and we also obtained the permission of CuCo to change the course and start anew. Our moderators work in a unique way. They both moderate the sessions and visualize what we do in the form of a drawing. You can see their drawings summarizing the differences in the same place as this report.

What's more - we understood that we had to work on two different levels in parallel to reach our goal in the end. These are the content and the process.

Hence, in the next meeting, we started from scratch. We wanted to understand how we define plasticity. So each participant brought their own definition of the terms, and we discussed what they taught us. Did we reach a common definition that will serve us in the following stages? Not necessarily so. It was just the beginning. Then, we discussed how to structure our research or how to construct our common research question. In addition, we discussed the possible dimensions of the project. For example, should education be part of our project?

In the next meeting, we discussed what should be the binding theme of the project. For example, should we look for one subject that we can circulate around (remember: Coffee), or should we work on several themes in parallel and connect them in novel ways (education, exchange, collective action).

What turned out to be clear is that plasticity is not a solitary term. It is immersed in a network of other terms that all possess an influence on the way the system work (e.g., robustness, adaptation, acclimation, etc.).

In the same meeting, on the process level, we also discussed what should be the outcome of the project. What do we expect to achieve? Is it something like a book? Should it be some traditional scientific projects? Several ideas were proposed. We also made the distinction between the outcome and output of the project.

Time passes fast when you enjoy it, and we enjoyed our time. However, we also had to start and close the spark grant project because the time allocated to it started to come to an end. So in the team's last meeting, we moved on to discuss opposing views about how to structure the grant proposal that we are about to submit to the CuCo. We presented two possibilities that we called monist and pluralist. Structuring the project according to the monist concept will mean that we will all have to work on one theme in the next phase of the project. Structuring the next phase as a pluralist project means that each one will work on the plasticity-related subject from his field, and the analysis and conclusions of how plasticity and its related network of terms can instruct plasticity of the social will be achieved from different types of interactions between the team members and other participants (e.g., through master student projects). We opted for the second option, and this is how we will structure our grant proposal that we will submit to the CuCo shortly.

If you want to learn more about our project, wait for the proposal and more so if it will be awarded.

To honor the understanding that plasticity works concomitant with a network of other concepts and our diverse backgrounds and fields, we present a word cloud below that summarizes our spark grant project.

Fig. 1: Our World of multiple meaning: Plasticity is not an isolated term. It is connected in an unshakable bounds to many other scientific and scholar terms. We would like to use our combined expertise to form connection between these terms and to understand how knowledge from different fields of study can be used to promote plasticity of our contemporary culture that faces repeated crises and challenges. How can academic studies from different fields promote plasticity of the social?